Treasury, ALM & Risk Platform

Implementation Whitepaper

Ready for implementation · Phase 0 executable

Scope basis: Tier 1 Bank Treasury — Instrument Universe & Granular Balance Sheet Taxonomy

30 artifacts · 17 bounded contexts · one adversarial review · two independent taxonomy validations

# Contents

Right-click and choose Update Field to build the contents.

## How to use this document

This whitepaper is the single consolidated specification for a treasury system of record with

integrated asset-liability management, liquidity, risk and regulatory reporting. It is self-contained

on architecture, data model, module contracts, delivery sequence, controls and acceptance criteria.

| Reader | Start at |
| --- | --- |
| Board / ALCO | Part I, then Part VII |
| Programme manager | Part VI, then Part VII |
| Solution architect | Parts II–IV |
| Implementation team | Part VI §3 (Phase 0 tickets), then Parts III–V |
| Vendor / procurement | Part I, Part VI §2, Part VIII |
| Audit / risk | Part V, Part VIII |

Design intent, stated once. Every figure the platform produces must be traceable to the individual

transactions that produced it and reproducible exactly as it stood on any past date. Everything else in

this document follows from that.

# PART I — SCOPE

## 1. What is being built

A platform that becomes the bank's system of record for treasury and the source of its ALM,

liquidity, risk and regulatory numbers. Treasury deals are booked, confirmed, settled and accounted for

here. Core banking remains the system of record for retail and corporate loans and deposits, which feed

the platform daily.

## 2. Scope decisions

Settled before design; everything downstream is constrained by them.

| Decision | Choice | Consequence |
| --- | --- | --- |
| Deliverable | Technology-agnostic architecture | Capabilities, boundaries and contracts specified; stack choices remain open |
| Regulatory regime | Basel III/IV + IFRS 9, single jurisdiction | No multi-GAAP; regulatory layer is a configurable rules engine |
| Legal entity | Single entity — provisional | Entity carried as an attribute; no consolidation built. Four unresolved signals — see Part VII §1.1 |
| System boundary | Full TMS + ALM + Risk | Core banking keeps loans and deposits |
| Scale | ~500k customer accounts | Contract-level storage and projection throughout; no cohorting |
| Hedge accounting | IFRS 9 only, no macro hedge accounting | One rule set. Structural hedges run economically. Capital consequence in Part V §6 |
| Net investment hedging | Excluded — blocked, not decided out | Requires a foreign operation; moves with the group-structure question |

Out of scope: loan origination and servicing, customer channels, the core banking GL itself, IFRS 9

ECL model computation (consumed via a specified interface), client-facing treasury sales.

## 3. Instrument universe

The full source Part 1: money market and central bank facilities; repo, reverse repo, tri-party,

securities lending and collateral swaps; fixed income including ABS/MBS, covered bonds, CoCos and

structured notes; FX spot, forwards, swaps, NDFs, cross-currency swaps and options **including barriers

and digitals**; interest rate derivatives including swaptions, caps, floors and futures; credit

derivatives including single-name and index CDS; equity and commodity instruments where mandated;

wholesale funding and issuance; liquidity and collateral tools; internal ALM instruments; and trade and

structured finance.

Exotic FX options are in scope. The source universe names barriers and digitals. This makes a

vanilla-only pricing library disqualifying rather than a trade-off.

# PART II — ARCHITECTURE

## 1. Seventeen bounded contexts in six layers

| Layer | Domains |
| --- | --- |
| L1 Platform Services | D16 Ingestion, Reconciliation & Data Quality · D17 Batch Orchestration & Operational Control |
| L2 Foundation | D1 Reference & Static Data · D2 Instrument & Position Core · D3 Market Data & Curves |
| L3 Execution & Operations | D4 Deal Capture · D5 Confirmation, Settlement & Payments · D6 Collateral & Securities Financing · D7 Accounting & Sub-ledger |
| L4 Valuation | D8 Valuation & Analytics Engine |
| L5 Analytics | D9 ALM & IRRBB · D10 Liquidity & Funding · D11 Market & Counterparty Credit Risk · D12 Funds Transfer Pricing |
| L6 Output & Governance | D13 Regulatory Reporting & Capital · D14 Scenario & Stress Framework · D15 Model Governance, Audit & Control |

The limit framework is not part of D11. It is a separate concern consumed by D4's pre-deal checks

and by D9, D10 and D11's outputs, and it lands with Phase 4.

Figure 1 — Seventeen bounded contexts in six layers. Solid = data flow; dashed = rule, state and query edges. Principal edges shown; the full set is enumerated in Part II §2

## 2. Three edge classes

The architecture is not acyclic, and pretending otherwise hides its most dangerous dependencies.

| Class | Direction | Carries | Made safe by |
| --- | --- | --- | --- |
| Data | Upward | Positions, cashflows, valuations, measures | Ordinary layering |
| Rule | Downward | Versioned, effective-dated definitions — never computed values | Versioning and effective dating |
| State | Downward | Observed state, sometimes externally asserted | Replayability — see below |

Rule edges: D7 → D2 (accounting classification); D13 → D2, D10, D6 (regulatory classification and

factor sets); D9 → D2 (behavioural models); D14 → D2, D8, D9, D10, D11 (scenarios, shocks and the

perturbation grammar); D15 → L5 (controls and validation).

The design rule that makes rule edges safe: a downward edge may carry only versioned,

effective-dated definitions. If it ever needs to carry a computed result, the boundary is wrong.

State edges: currently one — D6 → D2 encumbrance. A pledged bond leaves the HQLA buffer at the

moment of pledging. This is neither a versioned definition nor a computed result, so the rule above did

not constrain the edge most likely to be got wrong. A state edge is safe when the state is:

Event-published with effective and system timestamps — never a periodic file, because the

consumer recomputes on the event

Bitemporally queryable — "what was the state as of D, as known on K"

Provenance- and authority-tagged — how much of a reported number rests on externally-asserted or

operationally-maintained state must be a query

One read-only query edge — D10 → D6. The collateral optimiser needs current buffer composition and

whether the Level 2/2B caps are binding, which cannot be reduced to a rule. It does not break the design

rule because the rule governs what a lower layer stores and executes, not what it asks. The

discipline it needs is different: the optimiser stores no score, and every allocation records the policy

version, market snapshot and ratio state it was taken against.

## 3. Two boundary inversions

D6 originates Contracts. Central bank facility drawings are created from collateral pool state,

not booked by a dealer. The normal D4 → D2 flow inverts.

D6 encumbrance drives D2 classification, intraday. A collateral system publishing end-of-day

state does not degrade this — it stops the trigger firing, and HQLA becomes a batch number labelled

intraday.

## 4. Domain responsibilities

### L1 — Platform Services

D16 — Ingestion, Reconciliation & Data Quality. Feed adapters and canonical staging; acquisition

monitoring; data quality validation; the reconciliation engine and break register; quarantine and

suspense presentation; the data-good state D17 gates on. *Owns the fallback hierarchy for position,

balance and static feeds only — market observables belong to D3.*

D17 — Batch Orchestration & Operational Control. The pipeline DAG, scheduling and cut-off

management, gate evaluation, the provisional flag and its propagation, re-run semantics, calendar

awareness including regulatory reporting dates, run telemetry.

### L2 — Foundation

D1 — Reference & Static Data. Ten data domains: legal entity and organisation; counterparty and

customer master; product catalogue; calendars and conventions; index and benchmark definitions;

currency; GL chart and mapping; legal agreements and netting sets; classification rule sets;

bucket and vertex definitions. Everything is bitemporal.

D2 — Instrument & Position Core. The Contract and Balance store, the cashflow projection engine,

classification, position derivation, the bitemporal query surface.

D3 — Market Data & Curves. Fixings, FX, prices, credit spreads, volatility surfaces, curve

construction, multi-curve discounting, snapshot versioning, provenance tagging, the market-observable

fallback hierarchy. In Phase 0 because projection needs forward curves — not because of valuation.

### L3 — Execution & Operations

D4 — Deal Capture & Trade Lifecycle. Booking, amendments, novations, terminations, exercises,

fixings, rollovers; pre-deal limit checks; four-eyes authorisation.

D5 — Confirmation, Settlement & Payments. Confirmation generation and matching, settlement

instructions, nostro management, payment generation and release, failed-trade handling.

D6 — Collateral & Securities Financing. Repo and securities financing lifecycles, tri-party,

haircuts, margining, optimisation and substitution, central bank pool management. **Owns the encumbrance

register.** The only module straddling Phase 0 and Phase 4.

D7 — Accounting & Sub-ledger. IFRS 9 classification and measurement, effective interest,

modification accounting, hedge accounting, derecognition, IAS 32 presentation, the double-entry

sub-ledger.

### L4 — Valuation

D8 — Valuation & Analytics Engine. Narrow contract: given a position, a market snapshot and a date,

return value, cashflows, sensitivities and `exposure_by_bucket`.

### L5 — Analytics

D9 — ALM & IRRBB. Repricing gap, EVE, NII sensitivity, supervisory outlier tests, **definition and

calibration of behavioural models**, basis risk, CSRBB, IRRBB limits.

D10 — Liquidity & Funding. Cashflow ladder, counterbalancing capacity, LCR, NSFR, survival horizon,

funding concentration, encumbrance ratio, early warning indicators, funding plan, liquidity stress.

D11 — Market & Counterparty Credit Risk. VaR and expected shortfall, sensitivity aggregation and

P&L attribution, SA-CCR per netting set, PFE, CVA/DVA, settlement and issuer risk, large exposures

aggregation.

D12 — Funds Transfer Pricing. Internal pricing curves and transfer contracts.

### L6 — Output & Governance

D13 — Regulatory Reporting & Capital. Capital composition and the accounting-equity-to-CET1 bridge,

RWA, leverage, large exposures, the configurable returns engine, Pillar 3, capital planning. **Authors

the regulatory classification rules and factor sets** that D2, D10 and D6 execute.

D14 — Scenario & Stress Framework. All shocks, scenarios and stress paths, versioned and approved —

plus the transformation grammar that makes "consumed identically" mechanical: one representation,

node set, magnitude unit and floor rule, shared between D14's shocks and D8's sensitivity perturbations.

D15 — Model Governance, Audit & Control. Model inventory, validation, change control, four-eyes,

audit trail, reproducibility. Accretes from Phase 0; only the aggregate portfolio view is Phase 7.

# PART III — CANONICAL DATA MODEL

## 1. Six core objects

| Object | Definition |
| --- | --- |
| Contract | Legal and economic terms of a deal or holding. Common attributes as the query surface plus a typed terms payload per product family |
| Leg | One currency, one payment convention, one rate treatment. A Contract has one or more |
| Cashflow | Dated projection from a Leg. Tagged contractual/behavioural, principal/interest, certain/contingent |
| Balance | Carrying amount plus dimensions. No legs, no cashflows, no projection |
| Position | Aggregated view over Contracts and Balances. Always derived, never entered |
| Valuation | D8 output against a market snapshot. Immutable and versioned |

### 1.1 The Contract / Balance test

**A Balance is a position whose amount is asserted by an external system rather than derived from

terms the platform holds.**

Directly testable: can you compute this from what D2 holds, or must someone tell you the number?

|  | Objects |
| --- | --- |
| Contract — derived | Anything computable from held terms, including equity holdings (A.3, A.4) and short positions (B.4) as quantity legs |
| Balance — asserted | Vault cash, central bank reserves, nostro and vostro, ROU assets, associates and subsidiaries, PP&E, goodwill, tax, provisions, all equity lines |

Three properties this test buys:

It is stable under changing integration scope — object type does not flip as feeds are added

It subsumes the GL source/control rule: the GL is a source where the amount is asserted, a

control where it is derived. One test governs both the object model and the feed inventory

It applies at measure level as well as object level — a Contract may carry asserted measures (the

ECL allowance, an external pricer's fair value, externally-projected cashflows) alongside derived ones

It also gives the core-banking fallback a principled representation: if core banking cannot supply

contract-level terms, those positions are honestly Balances rather than Contracts with missing terms.

### 1.2 Derived values are never stored and never ingested

Accrued interest (A.15, B.13) and three of four reserve lines (FVOCI revaluation, cash flow hedge, FX

translation) are computed. Core banking also supplies accrued interest — **D2 computes it; core

banking's figure is a reconciliation control, not an input.** Ingesting both double-counts the balance

sheet and produces a GL break whose cause is architectural.

## 2. Leg rate treatments — five, not two

| Treatment | Instruments |
| --- | --- |
| Fixed | Money market, fixed bonds, IRS fixed leg |
| Floating (index) | FRNs, IRS, basis swaps, OIS. Three fixing states — see §5 |
| Return | Total return swaps, equity swaps — price appreciation plus distributions |
| Quantity | Commodity swaps and futures, short securities. Quantity × price; relaxes one-currency-per-Leg |
| Externally projected | ABS/MBS, index CDS, synthetic securitisation. Stored, not regenerated |

Worked decompositions. Interbank placement: 1 fixed bullet leg. Vanilla IRS: 2 legs. FX swap:

two linked Contracts, not one — a single Contract cannot carry two maturity dates. NDF: 2 notional

legs, settlement a single net cashflow. Repo: cash leg + collateral leg. **Collateral swap: collateral

legs both sides, no cash leg. Bond: 1 leg. ABS/MBS: 1 externally-projected leg.** Callable/CoCo/

barrier FX option: 1 leg + Optionality. TRS: return leg + funding leg. **Futures: no contractual

cashflows at all** — exposure only.

## 3. Fifteen classification dimensions, in two groups

Risk and behaviour (8): contractual maturity bucket · behavioural maturity · repricing basis and

index · currency · product/GL mapping · transaction counterparty · accounting classification ·

regulatory classification.

Presentation and accounting (7): book intent (trading vs banking — also the IRRBB scope boundary) ·

hedge designation · primary risk type · ECL stage · held-for-sale · capital instrument classification ·

issuer / obligor.

### 3.1 The counterparty split

counterparty_type splits into transaction counterparty and issuer / obligor. A bond bought from

Bank X but issued by a sovereign keys HQLA, risk weight, large exposures and concentration off the

issuer; settlement, confirmation and settlement risk off the trade counterparty.

**One dimension mis-classifies the entire securities book, and the direction depends on which field

survives — so the check must be built both ways:**

Trade-capture-derived data keeps the counterparty → understates HQLA, overstates bank concentration

Custody-derived data keeps the issuer → understates settlement risk

CRM substitution is the same failure one level down. HQLA keys off the issuer with no substitution;

risk weight keys off the post-substitution obligor. **The dimension is always the contractual

obligor**, with a derived crm_effective_obligor consumed only by the risk-weight rule. Guarantor stays

a Contract attribute — dimensions are derived and mandatory-complete; guarantor is captured.

### 3.2 Hard rules

No Contract or Balance is stored without a complete classification — but not_applicable is a

permitted value where a dimension is meaningless, and only ever as an explicit rule outcome

Classification is rules-derived, versioned and effective-dated. Override is four-eyes,

reason-coded, expiring and reported as a population

Every Contract and Balance carries an `internal` designation, and internal objects are excluded

from external-facing aggregation by construction. FTP generates two contracts per transfer netting

to zero at bank level; exclusion by report-level filter fails in the direction that inflates both

sides of the balance sheet by the full internal book

### 3.3 Bucket and vertex definitions are shared reference data

The maturity bucket dimension, D8's exposure_by_bucket and D9's repricing gap ladder must use **one set

of bucket boundaries, held in D1, versioned and effective-dated**. The gap is assembled from cashflows

plus exposure_by_bucket; bucketed independently the two halves do not add up, and the failure is

silent because each half looks reasonable alone.

A bucket is an interval; a vertex is a point. D1 holds one boundary set per family; derived vertex

sets store their derivation rule. The prescribed capital vertices are not derived — they must appear

exactly, and nearest-neighbour mapping is not permitted.

**The platform rate vertex set is the union of the 19 IRRBB band midpoints and the 10 prescribed capital

vertices — 29 nodes.** Both regulatory views are then exact subsets. The price is a sensitivity fan-out

~53% larger than originally assumed, which belongs in the performance envelope rather than being

discovered against it.

## 4. Cashflow is not the universal intermediate

Cashflow is the universal intermediate for liquidity, accrual and settlement. It is not for

repricing gap:

| Position | Contribution |
| --- | --- |
| Options | Delta-equivalent exposure via exposure_by_bucket — a swaption's cashflow rate treatment produces a meaningless bucket |
| Futures | Notional exposure, no cashflow |
| Equity, commodity, Balance-held | Contribute to EVE and NSFR with neither — excluded from the gap, with the exclusion stated |

## 5. Reproducible projection

project(Contract, as_of_date, basis, assumption_set, horizon,
        market_snapshot_version, reference_data_version) → Cashflow[]

Same inputs, same outputs, always. No ambient configuration, no hidden state.

Three fixing states, not two. A past reset is a stored fact; a future reset is a market query; and a

compounded-in-arrears current period is partly observed — some daily fixings existing and some not.

Now standard across the interest rate complex.

Determinism is asserted, not assumed. Bit-exact floating-point equality across a decade of platform

migrations is unsafe, and summation order changes when partitioning changes. Four measures:

Per-contract digest stored every EOD — converts a silently undetectable failure into one detected

next day at contract granularity. An aggregate comparison passes on compensating errors

Full detail frozen for regulatory reporting dates — 4–20 dates a year, ~100m rows

Engine builds retained as versioned artefacts. *For bought code this is a procurement requirement:

long-term version retention and escrow must be in the contract*

The regeneration test runs from Phase 1, not Phase 7

Monte Carlo needs its seed in the version set, or two runs differ by simulation noise.

The regeneration test is an implementation control, not a model validation. It asks whether the

platform reproduces the same number from the same inputs, and says nothing about whether the number is

right — a consistently wrong model passes it daily. Reproducibility is the precondition for validation,

not evidence of correctness.

## 6. Interfaces that were missing and are now specified

### 6.1 The ECL interface

| Direction | Content |
| --- | --- |
| Inbound | Allowance by contract, with measurement category |
| Inbound | Stage 1/2/3. Stage 3 interest is calculated on the net carrying amount, so D2's accrual is a function of the allowance — the ECL interface runs before accrual in the EOD sequence |
| Outbound | EAD for off-balance-sheet items, from D2's drawdown model |
| Outbound | Contractual and behavioural cashflows |

The allowance does not always reduce the carrying amount:

| Category | Effect |
| --- | --- |
| Amortised cost | Reduces it |
| FVOCI debt | Does not — carrying amount stays fair value; loss to P&L, entry to the FVOCI reserve |
| FVOCI equity | Not applicable — no impairment model |
| FVTPL | Not applicable |
| Off-balance-sheet | A provision liability in B.9, not a contra-asset |

Applying the allowance to an FVOCI debt carrying amount double-counts credit risk. The error is

invisible in aggregate — it looks like conservatism — and surfaces only when the FVOCI reserve fails to

reconcile against D7 and D9's CSRBB measure.

The external ECL model enters D15's inventory as a third-party model. Model risk does not stop at the

module boundary; if no validation evidence is available, the reliance is disclosed rather than assumed.

### 6.2 Legal agreements and netting sets

ISDA, CSA, GMRA and GMSLA are D1 static data defining netting sets, first-class because:

SA-CCR computes EAD per netting set. So does CVA

Gross-versus-net presentation for A.3 and B.4 depends on IAS 32 offsetting enforceability

LCR downgrade-trigger outflows are CSA rating triggers

D6 needs threshold, MTA, eligible collateral and rehypothecation rights

D11 needs the same CSA terms as SA-CCR formula inputs — margin period of risk, threshold, MTA and

independent amount enter the margined calculation directly

**The discount curve for a collateralised derivative is selected from the CSA, not the trade's

currency.** CSA paying interest on EUR cash → EUR collateral rate curve; uncollateralised → funding

curve; cleared → CCP rate

Terms must be structured data, not attached PDFs. Without structured eligible-collateral and

collateral-interest terms the platform cannot select a discount curve and cannot value a collateralised

derivative correctly — which makes the extraction a Phase 2 blocker, not a Phase 4 one.

### 6.3 The accounting-characteristics view

D7 must perform SPPI, closely-related and effective-interest assessments, all of which are legal-terms

analyses — but the terms payload is closed to it. **D2 publishes a derived accounting-characteristics

view**: payoff linearity, leverage, contingency features, embedded feature inventory, and

fee/discount/premium components. This preserves the instrument-agnostic property of the published

contract without widening the rule.

## 7. Accounting treatment

### 7.1 Classification and measurement

Business model is assessed at portfolio level; SPPI at instrument level. The rules engine needs

both scopes.

| Category | Measurement | Note |
| --- | --- | --- |
| Amortised cost | Cost less allowance |  |
| FVOCI debt | Fair value | ECL in P&L via OCI; recycles on disposal |
| FVOCI equity | Fair value | No impairment, never recycles |
| FVTPL | Fair value | Includes held CLNs failing SPPI |

**FVOCI debt and FVOCI equity behave oppositely on impairment and recycling and are routinely

implemented as one category. They are two enum values.**

Three cases routinely missed: Stage 3 interest on net carrying amount; POCI assets with a

credit-adjusted EIR; and modification accounting — a non-substantial modification requires

recalculating gross carrying amount at the original EIR with an immediate P&L catch-up.

### 7.2 Structured products — tiered

| Tier | Criterion | Structure | Build |
| --- | --- | --- | --- |
| 1 | Exercise right or trigger on the host's own terms | Single Contract + Optionality | Yes |
| 2 | Accounting separation required or embedded derivative carries a distinct risk type | Linked Contracts | Yes |
| 3 | Path-dependent or multi-underlying | Replicating portfolio | Specify only |

Barriers and digitals are Tier 1, in scope, priced by the bought library.

The two Tier 2 triggers are independent. IFRS 9 abolished bifurcation for financial assets

(4.3.2) but retained it for liabilities (4.3.3):

Held CLN — fails SPPI, whole instrument at FVTPL, no bifurcation. Tier 2 for risk visibility

Issued structured deposit — bifurcation applies **only if the embedded derivative is not closely

related. An unleveraged at- or out-of-the-money rate cap is closely related and is not separated**

The fair value option is not a free escape — own-credit fair value change goes to OCI, creating a

reserve line and a CET1 filter, and it never recycles.

### 7.3 Hedge accounting

IFRS 9 only, no macro hedge accounting. One rule set, no bright line anywhere.

| Retained | Forgone |
| --- | --- |
| Cost of hedging (FX basis, forward element) deferrable in OCI | Portfolio fair value hedging of the structural book |
| Aggregated exposures |  |
| Rebalancing rather than hedge failure |  |

Hedged items are frequently not Contracts — a portfolio layer, a forecast transaction, a risk

component, a net position. Hedge designation needs its own object; D2 carries only the queryable

designation dimension.

Documentation must exist at inception and cannot be retrofitted — captured at booking in D4 and

rejected if incomplete.

Two behaviours the system must enforce, not merely permit: rebalancing is mandatory when the hedge

ratio ceases to be appropriate; voluntary discontinuation is prohibited.

### 7.4 Derecognition

Repo'd-out securities are not derecognised; reverse-repo securities are not recognised but

do count toward HQLA if eligible and rehypothecable. Securitisation derecognition drives both the

balance sheet and D13's significant-risk-transfer conclusion — the two can legitimately diverge and both

must be recorded with reasoning.

# PART IV — RUN CYCLE AND OPERATIONS

## 1. The pipeline is a DAG, not a sequence

Liquidity depends on projection and reconciliation, not on valuation — so LCR can complete and

publish while a pricing problem holds up risk. Accounting depends on P&L, so a posting failure blocks GL

reconciliation and nothing else.

The rule: a stage blocks only its descendants, never the whole run. A linear pipeline blocks

everything downstream of any failure, which leads operations to override gates routinely — and a gate

that is routinely overridden has stopped being a control.

Figure 2 — The end-of-day pipeline as a directed acyclic graph. A stage blocks only its descendants

## 2. Two cycles, and their remedies

The callable book. D2's projection needs an exercise assumption; D8 cannot produce one without D2's

cashflows. Every callable, puttable, CoCo and Bermudan swaption sits in that cycle. Resolution: a

three-step protocol with a stored artefact in the middle — contractual projection → valuation →

re-projection under a versioned exercise assumption set. Break the cycle with **the prior day's

assumption set**, refreshed around exercise dates.

The collateral optimiser (Phase 4). Optimisation → encumbrance → classification → liquidity metrics

→ optimisation. Same remedy: score against the prior day's ratio state. What must not happen is

optimisation being wired into the ratio stage's own dependency chain, where the result depends on which

side of the recompute it ran.

## 3. Gates

| Type | Checks |
| --- | --- |
| Arrival | Feeds present, counts and control totals match |
| Validation | Quarantine volume within tolerance |
| Reconciliation | Unresolved break materiality within tolerance |
| Approval | Market snapshot and reference data version approved |
| Completion | Upstream finished, expected record counts produced |
| Plausibility | Day-on-day movement within tolerance — catches a completed-but-wrong stage, which completion checks structurally cannot |
| Model validity | No input depends on an unvalidated or overdue model |

Three outcomes: Pass · Warn (proceed, flagged provisional) · Fail (descendants blocked).

The model validity gate is a `Warn`, deliberately. Fail turns a governance lapse into an

operational outage and makes override irresistible; silent pass gives the control no teeth. Warn

computes the number, marks it provisional, and surfaces the overdue model in the daily provisional report

rather than in an incident.

Overrides require four-eyes, a reason code, justification, and automatic provisional propagation.

No override clears a reconciliation gate silently.

## 4. The provisional flag

Propagation is transitive through the DAG.

It must travel on the artifact, not the dashboard — rendered on the report, the export, the API

response and in the file name. A status page saying "today's run is provisional" does nothing once

someone has emailed a PDF.

It clears only by resolving the gate and re-running, never by hand, and the re-run produces a **new

version** rather than overwriting — because someone may have acted on the provisional figure.

## 5. The EOD window and compute budget

| Boundary | Time |
| --- | --- |
| Last essential input (core banking extract) | ~00:00 |
| First hard deadline (market open) | 07:00 |
| Window (W) | 7 hours, entirely unattended |

R + F + R ≤ W        R ≤ (W − F) / 2 = 3 hours

| Path | Budget |
| --- | --- |
| Tier A critical path | ≤ 90 minutes |
| Full pipeline | ≤ 3 hours |

R is the critical path, not total work. Keeping valuation and stress off the earliest-deadline path

is worth real design effort.

Tier A avoids the entire valuation subtree — cash and nostro position, funding requirement, limit

availability, ratio status. The LCR falls out cheaply because it is balance × prescribed factor, not

a valuation-dependent computation.

Figure 3 — The tier A critical path — what must exist by 07:00, and what it deliberately avoids

The unattended window is the design driver, not the duration. Automated retry first for transient

failures; paging escalation for the rest — the F = 1 hour assumption holds only with paging.

Instrument F from day one; it is the assumption most likely to be wrong.

## 6. Degradation order

| Tier | Outputs | Normal day |
| --- | --- | --- |
| A | Cash and nostro position, funding requirement, limits, ratio status | By 07:00 |
| B | Full LCR/NSFR, P&L, ALM metrics, risk measures (not as one class) | Same business day |
| C | Accounting postings, GL reconciliation, management reporting, FTP | May run late |
| D | Scenario and stress runs, non-regulatory analytics | Skippable, back-filled |
| Off-window | Counterparty exposure simulation — PFE, EPE, simulated XVA | Not a tier; larger than everything above combined |

Two date-dependent inversions, applied automatically from the submission calendar:

Regulatory reporting dates — regulatory output rises to tier A, and **no override may permit a

submission from provisional data**

Month-end — tier C rises to tier B. Month-end runs are longer *and* have tighter priorities, so

window pressure is worst when workload is heaviest. Load-test it explicitly

Two rules that keep degradation honest: a skipped output is an announced output; and **degraded

is not the same as provisional** — partial results and unvalidated results are different decisions with

different approvals.

# PART V — CONTROL ENVIRONMENT

## 1. Reconciliation

**The platform is the sub-ledger; the GL is the control account. Differences are exceptions to be

explained, never adjustments to be plugged.**

| # | Reconciliation | Available from |
| --- | --- | --- |
| 1 | Position to custodian/CSD — three-way | Phase 0 |
| 2 | Position to nostro — gates the tier A path | Phase 0 |
| 3 | Dual-mastered attributes (D1 golden source) | Phase 0 |
| 4 | Interim account-level GL comparison — daily trial balance extract | Phase 0 |
| 5 | Position to counterparty/CCP — valuation | Phase 2 |
| 6 | Sub-ledger to GL — posting-level | Phase 4 |
| 7 | Trade population to confirmation status | Phase 4 |

The custodian reconciliation is three-way, not two-way. A repo'd-out security remains a Position

while absent from the custodian statement; a reverse-repo security sits at the custodian without being a

holding. Comparing positions to holdings alone raises a false break on every repo, reverse repo and stock

loan in the book. The third leg is the encumbrance and financing register — **which gives the Phase 0

encumbrance register a second, independent justification beyond HQLA.**

A break is an object with a lifecycle, not a daily difference. The same break on five consecutive

days is one five-day-old break, not five. Resolution requires a stated cause — a difference that

vanishes because the data changed is still a break to explain.

## 2. Three failure classes, three responses

| Class | Response |
| --- | --- |
| Acquisition failure — feed absent or incomplete | Retry, then escalate. Downstream blocked |
| Validation failure — malformed, implausible, referential integrity | Quarantine to suspense; the rest proceeds |
| Reconciliation break — well-formed but disagrees with an external record | Break register; blocks by materiality |

The most dangerous is a partial acquisition that looks successful. A core banking feed arriving with

60% of records is worse than one that fails, because the balance sheet simply shrinks and nothing alerts.

Record counts and control totals are mandatory on every feed.

## 3. Quarantine presents, never excludes

A record failing validation or classification routes to a reported suspense position, and every

balance sheet and ratio report renders an unclassified line even when zero. Excluding the record does not

make ratios quietly wrong — it makes the balance sheet not balance by an amount nobody can name.

The same principle applies to risk, where the absent record is a risk factor. A position whose risk

factors are not in the historical dataset raises no error in a historical simulation: an absent factor is

a flat series, which reads as a position with no risk. **A position with incomplete factor coverage

is reported uncovered, never as zero-risk**, and the uncovered proportion of the book is published.

## 4. Provenance — three kinds

| Provenance | Answers |
| --- | --- |
| Market data | Observed, interpolated, stale, proxied, model-implied or manually marked — and it survives aggregation |
| Encumbrance | Externally asserted and authoritative (tri-party) · externally asserted and reconcilable · platform asserted · operationally maintained (standing state with no feed) |
| Models | Which models contributed to an output and their validation status |

Each answers a question that is otherwise an investigation rather than a query: *how much of this ratio

rests on non-observed prices* · *how much of the unencumbered buffer rests on operationally-maintained

state* · what share of our EVE rests on a model overdue for revalidation.

## 5. Governance

Four-eyes is a platform service, not a per-module feature. Nine controlled actions are live in Phase

0 alone. Implemented per module it becomes several approval mechanisms with different override semantics

and no consolidated answer to "what was overridden yesterday, by whom, and what is still outstanding" —

the first thing an auditor asks for.

The Phase 0–3 segregation model is not front/middle/back office, which presumes D4 and D5. Until

Phase 4 the meaningful separation is between those who author reference data and rules and **those who

consume the outputs**: the maintainer of a counterparty rating must not be the person whose ratio

improves when it changes.

The impact statement is a capability, not a document. Retroactive-effect changes must state *what

reproduces differently, and over what period* — required for calendars, snapshot restatements and rule

activations. It means applying a proposed change without committing it, re-running against a frozen

population and diffing in taxonomy lines, balance moved and ratio buckets. It is a real Phase 0 build

item and the highest-leverage control in the platform: it turns "we think this rule change is fine"

into a number, before production rather than after.

Every audit record carries a correlation ID. One business action spans several modules — a back-dated

trade correction touches D2's bitemporal store, triggers a classification recompute, changes a

reconciliation outcome, flags a re-run and later produces an accounting adjustment. Six records in five

modules describing one decision. The ID cannot be retrofitted.

Model governance. The inventory is far larger than it appears — about eight things are named as

models across the design corpus; there are at least twenty-six. The unnamed ones cluster in proxy and

fallback hierarchies, the proxy spread model, the core/volatile deposit split, the collateral outflow

proxy, PFE and XVA, and the external ECL model. A proxy is a model. Backtesting applies to roughly a

third of the inventory — EVE has no realised outcome and neither does a curve — so **validation technique

is an inventory field. Approved usage is a list of named consumers and purposes, not free text.**

BCBS 239 is the governing standard for reconciliation and data quality.

## 6. The capital consequence of the hedge accounting decision

Stated here because it runs against intuition and belongs in front of the Board.

| Approach | Where volatility lands | CET1 impact |
| --- | --- | --- |
| Cash flow hedge accounting | CFH reserve (OCI) | None — filtered out of CET1 |
| No hedge accounting | P&L → retained earnings | Direct — retained earnings *is* CET1 |
| Micro fair value hedge | P&L both sides | Minimal |

Basel's cash flow hedge reserve filter exists precisely to keep economically meaningless hedge volatility

out of capital. Declining hedge accounting declines that protection.

The risk is unchanged; only its presentation and capital treatment differ. Two mitigations remain

available and should be prioritised on capital grounds: micro fair value hedges of specific

issuances, and cash flow hedges of forecast interest cashflows. **The revisit threshold is CET1

volatility, not earnings volatility, and the former binds first.**

Hedge designation cannot be applied retrospectively — adopting macro hedge accounting later works

prospectively only, and the volatility already taken is not recoverable.

# PART VI — DELIVERY PLAN

## 1. Phase sequence

The organising move: separate rule *authoring* from module *completion*. A later-phase module can

author a versioned rule set that an early-phase module executes.

| Phase | Delivers | Usable output | Posture |
| --- | --- | --- | --- |
| 0 Foundation | D1 (agreements, netting sets, bucket definitions), D2, D3 (snapshot, fixings, FX, projection curves), D16, D17, classification rules engine with interim authorship staffed, D15 control core incl. impact-statement dry-run, D6 minimal encumbrance register at full-D6 grain | A complete, classified balance sheet with contractual cashflows, reconciled and orchestrated | Build D1/D2/D3. Buy the D16 matching engine and D17 orchestrator; build the adapters |
| 1 Liquidity | D10 ladder, LCR, NSFR, HQLA, concentration; D13 factor rule sets; D15 regeneration test | Daily regulatory liquidity ratios | Build |
| 2 Valuation | D8 pricing, curves, sensitivities, exposure_by_bucket | Independent valuation, daily P&L | Buy the pricing library |
| 3 ALM & IRRBB | D9 gap/EVE/NII, behavioural models, D14 scenarios, internal liquidity metrics | ALCO pack, IRRBB, internal stress view | Build the framework; own the models |
| 4 Front-to-back | D4, D5, full D6, D7 — bought. Built regardless: the limit framework, D11's counterparty carve-out, the D6 register handover (§3.2) | Treasury as system of record; STP | Mostly buy — a buy-evaluation contract and a procurement workplan, not a build spec |
| 5 Risk | D11 VaR/ES, stressed VaR, attribution, backtesting, PFE, full XVA | Full market and counterparty risk | Buy the analytics |
| 6 FTP & Regulatory | D12, D13 full returns engine | Business-unit performance, regulatory submission | Build |
| 7 Governance | D15 aggregate model risk — inventory-wide reporting, risk appetite, model provenance | Audit and regulator ready | Build |

Phase 7 is not "D15 (full)". Inventory, validation and change control accrete from Phase 0.

Models arrive from Phase 0 onward, and validation-before-first-use means the capability must exist when

each model does. A validation function arriving in Phase 7 validates nothing for six years and then

inherits a portfolio of production models nobody approved. **The revalidation cycle starts with the

second model, not with the governance phase.**

Principal risk: Phase 4 is where these programmes die. More work than everything else combined, and

it delivers operational efficiency rather than new insight.

## 2. Build / buy

| Component | Posture | Reasoning |
| --- | --- | --- |
| D1, D2, D3 | Build | The bank's specific structure; poorest off-the-shelf fit |
| D16 matching engine, D17 orchestrator | Buy; build the adapters | Mature vendor market; nothing here is a differentiator |
| Pricing library (D8) | Buy | Validating pricers across the full instrument range is a multi-year specialist commitment with no competitive return. Must price barriers and digitals |
| Phase 0 curves | Consume vendor-published; build in-house from Phase 2 | Calibration needs the Phase 2 library |
| Phase 4 front-to-back | Evaluate seriously for purchase | Commodity, high volume, unforgiving |
| Risk analytics (D11) | Buy the analytics; build the limit framework | As valuation |
| D13 returns engine | Build | Must be configurable to the local regulator |

Two procurement requirements that will otherwise be missed: long-term version retention and escrow

for the pricing library, because reproducibility requires running a decade-old vendor build; and

raw quotes rather than derived factors when buying market data history.

## 3. The delivery plan across all seven stages

112 discrete pieces of work. Each stage is cut into waves, and **each wave leaves the platform in a

working state** — not a partially built one.

| Stage | Pieces | Note |
| --- | --- | --- |
| 0. Foundation | 16 | Detailed in §3.1 |
| 1. Liquidity | 16 | Does not finish liquidity — see below |
| 2. Valuation | 16 | Spine is the library procurement, not a build |
| 3. ALM & IRRBB | 16 | Gated by the CSRBB scope decision |
| 4. Front-to-back | 8 | Carve-outs only — the rest is a procurement, §3.2 |
| 5. Risk | 16 | Excludes the counterparty measures carved out to Phase 4 |
| 6. FTP & Regulatory | 16 | Cannot be sized without the returns inventory |
| 7. Governance | 8 | Deliberately the smallest — see below |

Every stage ends with an operational readiness item — parallel running, cutover, rollback, training

and operational acceptance. These were added after an internal critique found 97 build tickets with no

cutover or acceptance anywhere in the programme. The omission is worth recording, because it is the

normal way a technically successful programme disappoints its users.

Stage 7 being smallest is a design achievement, not an omission. The review found model governance

scheduled at the end — meaning that for six years models would produce numbers the bank relied on with

nobody having approved them, and the governance function would inherit a portfolio it had never seen.

Approval and validation now happen in every stage, as each model is built. What remains at Stage 7 is

the portfolio view — how much of what we report rests on models we have not validated — which

genuinely cannot be built until there is a portfolio to look at. **Two of its eight items are checks

that the correction held.**

Stage 1 does not finish liquidity. It delivers the regulator's ratios, which are computable from

prescribed rules. The bank's own view of what would happen under stress needs behavioural models and

arrives at Stage 3. Stated plainly because the alternative reading — "liquidity is done" — would be

wrong for two years.

### 3.1 Stage 0 execution — sixteen tickets in six waves

| Wave | Tickets | State at the end |
| --- | --- | --- |
| 1 | P0-11 control core · P0-15 rule authorship (non-engineering) · P0-01 reference data | Static data versioned and governed; rule authoring staffed |
| 2 | P0-02 agreements & netting sets · P0-03 object store · P0-04 market data · P0-08 ingestion | Objects store and ingest; snapshots exist |
| 3 | P0-05 projection · P0-06 classification engine · P0-09 reconciliation · P0-10 encumbrance register | Cashflows project; objects classify; feeds reconcile |
| 4 | P0-07 position derivation · P0-12 orchestration | Positions at both freshness levels; pipeline runs gated |
| 5 | P0-13 retention & regeneration test · P0-14 balance sheet projection | Reproducibility proven; Phase 0 technically acceptable |
| 6 | P0-16 operational readiness | The phase is operationally live — parallel run explained, on-call exercised, forums standing |

**Wave 6 exists because the breakdown originally declared deployment and monitoring tickets out of

scope.** That was defensible for one foundation phase and was then inherited unexamined across six

further phases, producing 97 build tickets with no cutover, parallel run, rollback, training or

operational acceptance anywhere in the programme.

**Phase 0's operational change is narrower than later phases — and it sets every habit the rest of the

programme inherits:** a nightly pipeline whose gates can block; a break register that ages and

escalates; a suspense presentation that leaves unclassified balances on the balance sheet; four-eyes on

static data from the first record; and a balance sheet generated rather than assembled.

Two acceptance criteria worth stating at programme level: the generated balance sheet runs in

parallel with the current process for a stated number of cycles with **every material difference

explained, not merely reconciled; and the on-call rota is exercised, not designed** — a failed gate

at 2am has actually been handled before go-live.

Figure 4 — Phase 0 ticket dependencies across six waves

P0-11 and P0-15 come first deliberately. Four-eyes on static data is required from the first record,

not retrofitted — and the control core carries the impact-simulation harness that D1 and the

classification engine both assume exists. Rule authorship is subject-matter work with a long lead time;

the engine ships empty without it.

P0-06 is the largest and highest-uncertainty ticket. It carries rules-as-data with bitemporality,

precedence, explainability, impact simulation, the fifteenth dimension, the CRM substitution split and

a second customer-aggregation pass (§3.1.1 below).

#### 3.1.1 Classification runs in two passes

Part of regulatory classification is irreducibly customer-level. Deposit insurance coverage is a

per-depositor threshold; operational deposit status is **capped at the amount required for the

service; connected-counterparty grouping spans accounts. So B.3 — customer deposits, the largest

liability line — cannot be classified contract-by-contract.**

Pass 1   per-Contract rule evaluation
Pass 2   customer aggregation → threshold and cap computation → allocation back to Contracts

Three things must be deterministic, stated and versioned:

The threshold — insurance limit and operational-service cap

The allocation rule — which contracts receive the insured portion. If implicit, the

insured/uninsured split moves between runs and the LCR moves with it, with no attributable cause

The sequencing — insurance-first gives a different split from operational-cap-first

This does not undercut contract-level storage, which remains necessary but is not sufficient.

#### 3.1.2 Recompute triggers

Classification changes without anything happening to the contract. Seven triggers, of which two are

routinely missed:

Passage of time — a 13-month deposit enters the ≤12-month bucket tomorrow with no event at all

Encumbrance change — intraday, event-driven

Plus counterparty static change, ECL stage migration, management decision, rule version activation

(rare, high impact, requires an impact statement before activation), and behavioural recalibration.

There is no default outcome. An unmatched object is unclassified and routes to suspense. A

default of "banking book" or "amortised cost" makes the batch run clean and produces a balance sheet that

is confidently wrong. An unclassified line is ugly, and being ugly is its function.

### 3.2 Stage 4 is a procurement, and only its carve-outs are planned

Breaking Stage 4 into build tasks would pre-empt the buy decision. Writing several thousand build

requirements for software the bank would prefer to purchase is wasted effort and a strong institutional

bias toward building it anyway. What exists instead is a buy-evaluation contract — what a candidate

must satisfy, which requirements are pass/fail, and how a supplier's claim is converted into evidence

rather than accepted as a claim — plus a procurement workplan covering lots, calendar, decision

rights and stop conditions.

Three pieces are built regardless of the outcome, and they are the eight tickets in the Stage 4 count:

| Carve-out | Why it is not in a lot |
| --- | --- |
| The limit framework | Marked Build because no vendor sells the shape — limits spanning treasury positions, banking book measures and counterparty exposure, evaluated pre-deal |
| The counterparty carve-out | Current exposure, SA-CCR, a simplified netting-set CVA and settlement exposure. Rests on Stage 0–2 foundations, not on the package or on Stage 5's simulation |
| The collateral register handover | Full collateral management arrives around a register that has been in production for two or three years. The handover is inheritance, not installation |

All three can be built during the procurement. None depends on the vendor, the lots or the contract,

and the procurement runs roughly nine to twelve months from gate to signature. Two consequences:

It de-risks the stage the programme names as its principal risk by shortening what remains after

signature

It strengthens the fallback. One stop condition is "cost exceeds the build estimate" — a limit

framework and a counterparty exposure engine already built are cost removed from that alternative,

priced rather than estimated

Two things the carve-out set deliberately excludes: package implementation, which cannot be written

without presupposing the award; and the deal capture and settlement module specifications, which become

necessary only if the buy fails.

Two failure modes the carve-out tickets exist to prevent. A pre-deal check that is not on the booking

path is decoration — if the package books first and checks after, the framework detects breaches instead

of preventing them, which a post-deal report already does. And **the register must remain the system of

record with the package publishing into it**: inverting that loses the bitemporal history, degrades the

intraday classification trigger to a batch file, and restarts the 24-month liquidity look-back — a

loss invisible in the ratio itself, which simply reports a smaller maximum and a better number.

## 4. Four clocks running now, independent of funding

Each loses value permanently for every month deferred. None depends on the platform.

| Clock | What is lost | Fix |
| --- | --- | --- |
| Collateral movement history | One month of the 24-month LCR look-back, permanently. Statement retrieval ages from self-service into archive request | Log forward (7 fields, named daily owner) · reconstruct backward from nostro, counterparty and custodian statements · proxy the residual conservatively |
| Legal agreement extraction | Lead time against a Phase 2 need | Structured extraction across tiers 1, 2 and 4 of the counterparty population |
| Market data history | Nothing — but this is the only one money can fix | Buy a vendor history set; raw quotes, not derived factors |
| FTP methodology | The only recoverable one — the inputs survive, the decision does not | Settle at Stage 4. Deferring means Stage 6 applies a newly chosen methodology backwards to two years of booked business, restating business unit performance for periods already reported |

The collateral and legal exercises share a population and should be run as one workstream with

separate tracks: statement requests issue on day one for everyone, agreement extraction proceeds in

tier order. The saving is coordination and relationship overhead, not extraction effort.

### 4.1 Seven pieces of work no engineer can do

The binding constraint is subject-matter capacity, not engineering capacity, and the detailed plan

quantifies it: seven of the pieces of work sit on the critical path and cannot be done by the build team.

| Work | Who | Blocks |
| --- | --- | --- |
| Accounting and regulatory classification rules | Finance and regulatory reporting | Stage 0. The platform classifies every position by these; without them it computes nothing |
| Prescribed liquidity factors | Regulatory reporting | Stage 1. The ratio engine ships empty |
| Ownership of the market risk conventions | Risk, as a named interim role | Stage 1 — but its deadline belongs to Stage 2. The conventions must be settled before the valuation library is bought, because the supplier's conventions are part of what is purchased. The tightest deadline in the programme and the least obvious owner |
| Supplier contract terms — retention, escrow, extractability | Procurement and Legal | Stage 2. Long-term rights that cannot be added later, from a position of dependency |
| Transfer pricing methodology | Finance with ALCO | Stage 4, used at Stage 6 |
| Regulatory return inventory | Regulatory reporting | Stage 6. The build cannot be sized without the list |
| Model validation resourcing | Executive — budget and hiring | Every stage from 2 onward |

None can be accelerated by adding engineers, and each has a lead time measured in months. They

should be resourced and started on their own schedule, ahead of the engineering that depends on them.

Legal agreement extraction is an eighth item of the same kind, sitting outside the numbered work

because it is a legal review rather than a platform task.

# PART VII — DECISIONS REGISTER

38 decisions gate the stages, and they are the programme's real critical path. None is engineering

work. Most are routine and belong to management; those below are the ones the Board or its committees

must take, or where deferral has a consequence the Board should see.

## 1. The four that go first

Each is factual or near-factual, has the longest lead time, and fans out across multiple phases.

### 1.1 Group structure — Board — now

Does the bank have subsidiaries, securitisation vehicles or foreign operations that consolidate? **Four

independent signals in the bank's own taxonomy say yes**; the scope decision says single entity.

| Signal | Line |
| --- | --- |
| Investments in associates and subsidiaries | A.9 |
| Non-controlling interests | C.6 |
| Own securitisation notes on balance sheet | B.6 |
| Foreign currency translation reserve | C.4 |

Fans out to D2's entity model · D7's net investment hedging and the FCTR · **D13's entire

consolidation and reporting scope** · D6's collateral scope.

Carrying the entity field costs one column now. Adding it later is a restatement, not a migration.

### 1.2 Trading book size — Treasury — now

Factual and answerable today. Sizes the whole of Phase 5 and the risk analytics procurement. If the

trading book is small and simple the Phase 5 build shrinks materially — worth knowing before the

procurement, not after.

### 1.3 CSRBB scope — Risk, with ALCO — before Phase 3

One answer, three artifacts — the measure (D9), whether spread curve infrastructure is needed (D3),

whether spread scenarios exist (D14). Plus D13, because CSRBB is a capital measure: spread moves on

the FVOCI portfolio flow through OCI into CET1 without ever appearing in P&L.

### 1.4 Validator sourcing — Executive, with Risk — now

Does an independent model validation function exist, and if not, how is validation sourced — internal

function, external firm, or rotating peer review?

Filed under Phase 7; needed now. Model governance accretes from Phase 0. It is a **budget and hiring

decision, not a build decision**, which is exactly why it needs runway. The scarcity problem is real at

this bank's size: independence is hard when the modeller and validator are the same two people in

rotation.

## 2. By owner

| Owner | Decisions |
| --- | --- |
| Board | Group structure (now) · SA or IRB · endorse staged funding |
| ALCO | EOD window and degradation sign-off · stress scenario approval workflow · CSRBB · FTP at all, and matched-maturity or pooled · hedge accounting ratification |
| Finance | GL authoritative source and posting interface · fair value option usage · IFRS 9 transitionals · snapshot timing and restatement · CVA-free fair value policy · confirm the trade-date election · author the interim accounting rule set |
| Treasury | Trading book size (now) · collateral log ownership (now) · uncleared margin IM scope · rehypothecation, CCP membership, covered bonds, CB facilities · significant currency threshold · NMD history and deposit beta · exotic FX sequencing |
| Risk | CSRBB · validator sourcing (now) · interim non-rate grammar owner · overlay semantics · VaR method · exposure simulation cadence · Tier 3 path · history purchase (now) |
| Regulatory Reporting | Deposit insurance threshold and aggregation · returns list, templates and calendar · SA/IRB · confirm standardised market risk means sensitivities-based · author the interim regulatory rule set |
| IT / Vendor | Incumbent TMS extract capability (now) · core banking extract capability (now) · curve build-or-buy · library retention and escrow |
| Operations | On-call rota and paging · auto-retry policy · own the daily collateral log |
| Legal | Agreement extraction ownership · commission netting opinions where gaps are found |

## 3. Three decisions whose real deadline is earlier than their filed phase

| Decision | Filed | Actually needed | Why |
| --- | --- | --- | --- |
| GL authoritative source and posting interface | Phase 4 | Phase 0 wave 2 | The GL is a source for 18 of 40 balance sheet lines. C.3 retained earnings is the balancing figure and has no other source |
| Validator sourcing | Phase 7 | Now | Governance accretes from Phase 0 |
| Fair value option usage | Phase 6 | Phase 0 rule authoring | Changes the accounting classification rules being written now; brings own-credit OCI and its CET1 filter into scope |

**The pattern: a decision was filed under the phase that consumes it most visibly, rather than the phase

that first depends on it.** Worth re-checking the remaining twenty-nine as each phase is broken down.

## 4. Settled

| Decision | Outcome |
| --- | --- |
| Ingestion granularity | Contract-level storage and projection; no cohorting |
| Retention | Store inputs and as-reported outputs permanently; regenerate projections. Lifetime + 7 years; shared inputs permanent |
| Structured products | Tiered rule; Tiers 1 and 2 built |
| Intraday freshness | Near-real-time with EOD authoritative cut and per-source freshness stamping |
| Hedge accounting | IFRS 9 only, no macro — capital consequence in Part V §6 |
| Multi-entity | Entity field carried, machinery not built — provisional |
| NCD routing | Negotiability. All negotiable CDs to B.6; B.3's NCD sub-line deleted |
| Recognition | Trade date, FX spot in the derivative lines (confirm against existing policy) |
| Taxonomy additions | Seven additions, one deletion — see Appendix B |

Unowned decisions do not age into being decided. If one sits open for two months without its named

owner disputing the assignment, the assignment is probably wrong.

# PART VIII — ACCEPTANCE CRITERIA

## 1. The three coverage tests

Applied at Phase 0 exit. The third was originally missing, which is how bankers' acceptances, equity

holdings, collateral swaps and physical commodities went unnoticed.

Every Part 1 instrument class books, projects and prices — validated against the worked

decompositions, including NDF net settlement, FX swap as two linked Contracts, repo recognition

rules, collateral swaps with no cash leg, tri-party baskets, callable CoCos, inflation-linked

notionals, TRS return legs, commodity quantity legs, futures with no cashflows, and

externally-projected ABS/MBS

Every Part 2 line generates as a *(measure, predicate)* pair over Positions and Balances, against

a declared measure set, with no bespoke rule

**Every Part 1 class maps to a named Part 2 line, or is explicitly recorded as an intentional

non-appearance with a reason**

### 1.1 Why test 2 needs a measure, not just a predicate

Six lines need a sub-contract split — one contract contributing different amounts to two lines:

| Split | Lines |
| --- | --- |
| Revolver drawn vs undrawn | A.6 / D.1 |
| Overdraft balance vs limit | A.6 / D.1 |
| Card balance vs limit | A.6 / D.1 |
| Partially-designated hedges | A.3 / A.8 |
| Deposit operational vs non-operational portion | B.3 |
| Deposit insured vs uninsured portion | B.3 |

No dimension set closes this, including the fifteen-dimension set. The problem is not which slice you

filter on. Declared measures: drawn amount, undrawn amount, limit, gross carrying amount, fair value,

notional, designated portion.

## 2. Further Phase 0 criteria

Contractual and behavioural projections coexist; their difference is explainable per contract

Any historic position, balance or cashflow set reproduces exactly on both temporal axes, under the

models, rules, reference data and classifications in force at the time — verified by the Phase 1

regeneration test against per-contract digests

Schedule generation passes an exhaustive convention test suite, **including partial-observation

compounded RFR periods**

No object exists without complete classification; not_applicable only where genuinely meaningless;

overrides four-eyes and reported

Projection completes within the EOD window with re-run headroom, sized on the assumption that **the

floating-rate book invalidates its cache daily and that internal contracts multiply the contract

count**

Balance derivation branches on measurement category for ECL — verified by reconciling the FVOCI

reserve against D7 and D9's CSRBB measure

A rule change is a data change with no code release; the release boundary is crossed only when a

rule needs a predicate outside the declared input vector

Conflicting rules at equal precedence block activation

Explanation is a stored lookup, not a reconstruction, at both object and population level

Impact simulation runs before any rule activation

Encumbrance changes propagate to HQLA eligibility without a batch delay

The provisional flag renders on the artifact, surviving export outside the platform

## 3. The three tests a non-technical reader can apply

Point at any figure in any report and ask why. The answer should be a rule, a version, the inputs

that satisfied it, and who approved it — in one query, not a research exercise

Ask for a report as it stood three years ago. It should reproduce exactly, under the rules,

assumptions and data that applied then

Ask why a ratio moved. The answer should decompose into balance sheet change, market change and

assumption change, separately

A platform that cannot do these three is a reporting tool. One that can is a control environment.

# APPENDIX A — Instrument to module traceability

All classes flow through D2, D7, D9/D10 and D13; the table names modules with material specific

handling.

| Part 1 class | Modules | Notes |
| --- | --- | --- |
| 1. Money market | D4, D5, D10 | Central bank facilities also D6, which originates them |
| 2. Repo & securities financing | D6, D4, D5, D10 | Recognition rules mandatory. Tri-party collateral is a basket reallocated daily by the agent, not known ISINs. Collateral swaps have no cash leg |
| 3. Fixed income | D3, D8, D6, D11 | ABS/MBS externally projected. CoCos and callables use optionality |
| 4. FX | D8, D11, D5 | FX swaps are two linked Contracts. Barriers and digitals in scope, priced by the bought library |
| 5. Interest rate derivatives | D8, D9, D11, D6 | Futures generate no contractual cashflows. TRS uses the return treatment |
| 6. Credit derivatives | D8, D11, D13 | Index CDS externally projected. SA-CCR and CVA per netting set |
| 7. Equity & commodity | D8, D11, D6 | Commodity legs are quantity × price. Equity swaps use the return treatment |
| 8. Wholesale funding issuance | D4, D7, D10, D13 | AT1 routes to B.7 or C.5 by capital instrument classification |
| 9. Liquidity & collateral tools | D6, D10 | Facilities received have no balance sheet anchor — separate register, memorandum in D.8 |
| 10. Internal ALM instruments | D12, D9, D2 | Carry the `internal` designation; excluded from external aggregation by construction |
| 11. Trade & structured finance | D2, D10, D13 | Forfaiting and factoring are funded purchases of receivables at a discount, not contingent exposures |

# APPENDIX B — Balance sheet taxonomy resolution

Part 2 is the reporting projection of the canonical model. Line-by-line validation was run twice,

independently; both runs agree the Balance primitive is required.

Composition: 12 lines pure Contract · 16 pure Balance · 8 mixed · 4 derived-dominant. *Counts move

with the equity call, now settled as Contract.*

## Four "orphans" that were not orphans

Resolved by splitting by role rather than by adding lines.

| Instrument | Resolution |
| --- | --- |
| Bankers' acceptances | Three presentations of one name: held → A.4 (A.3 if trading) · accepted unfunded → off-balance-sheet with ECL provision in B.9 · accepted and discounted → A.6 |
| Securities lending | Securities lent remain in A.3/A.4 encumbered; received securities not recognised; cash collateral → extended B.5 |
| Collateral swaps | Net balance sheet impact nil — the entire substance is encumbrance, disclosed in D.5/D.6 |
| Committed facilities received | Not recognised — a facility granted to the bank is not an asset. Memorandum in D.8 |

## Seven additions, one deletion

| Change | Content |
| --- | --- |
| A.3b (new) | Non-trading financial assets mandatorily at FVTPL. A.3 is the trading book — filtering it on FVTPL swept banking-book CLNs into the trading book, wrong for IRRBB scope, market risk capital and disclosure. Separately required by IFRS 7 |
| D.5, D.6 (new) | Assets pledged as collateral; collateral received that may be repledged. Required by LCR, NSFR and IFRS 7 |
| D.7, D.8 (new) | Acceptances and endorsements; facilities received (memorandum) |
| B.5 (extended) | "Repurchase agreements and cash collateral received on securities lending" |
| A.15 (sub-components) | Precious metals (not HQLA under Basel III); exchange and clearing house margin — settled-to-market VM extinguishes daily and creates no balance, so treating it as a receivable overstates both the balance sheet and the leverage exposure measure |
| B.3 (deleted) | NCD sub-line removed |

## Routing rules and boundaries

NCDs — negotiability. All negotiable CDs to B.6. *Accepted cost: NCDs placed with retail or SME

customers receive debt-security ASF rather than deposit treatment*

Promissory notes — negotiable and held-to-collect-and-sell → A.4; bilateral and non-traded → A.6

Syndicated participations, borrowing side — syndicated loan → B.2; syndicated note → B.6

A.2 / A.5 — A.2 is settlement and cash management (nostro, current, overnight, call); A.5 is term

lending to banks. Aligns with the LCR's operational/non-operational distinction, so one rule serves

presentation and the ratio

## Three intentional non-appearances

Internal ALM contracts (eliminate on consolidation) · collateral swaps (encumbrance only) · facilities

received (not an asset).

# APPENDIX C — Supporting document set

This whitepaper consolidates the following. Each remains authoritative for its own depth.

| Artifact | Covers |
| --- | --- |
| treasury-alm-risk-platform | Architecture blueprint (rev 3) |
| d1-reference-and-static-data … d17-batch-orchestration | Sixteen module deep-dives |
| classification-rules-engine | The Phase 0 capability spanning D1, D2 and later-phase rule authors |
| rate-transformation-grammar | Shock and sensitivity representation |
| part2-taxonomy-mapping · part2-query-specification | Two independent line-by-line validations |
| taxonomy-policy-decisions | The accounting policy resolutions in Appendix B |
| eod-window-and-degradation | The operational contract in Part IV §5–6 |
| counterparty-documentation-workstream · statement-request-pack | The pre-build clocks in Part VI §4 |
| phase4-front-to-back-buy-evaluation | What a candidate front-to-back system must satisfy |
| phase4-procurement-workplan | Lots, calendar, decision rights, waiver rule and stop conditions |
| gl-interface-decision | GL authority and posting interface granularity |
| tickets · tickets-phase1 … tickets-phase7 | Eight executable ticket sets — 112 pieces of work. tickets-phase4 covers the build carve-outs only |
| decisions-register · phase-breakdown-readiness | Part VII in full |
| architecture-critique · phase-breakdown-critique | The adversarial reviews that reshaped the design and the plan |
| blueprint-amendment-protocol | How seven agents amended one blueprint without collisions |
| executive-summary · programme-delivery-summary | Board and ALCO summaries — what and why, then how it will be delivered |

## Closing note on how this design was produced

The architecture was independently and adversarially reviewed, and the review changed it materially —

the Balance primitive, two missing domains, the phase re-cut, the fifteenth dimension and the

customer-aggregation pass all came from challenge rather than from the original design. The parts that

survived unchanged were the parts held with least confidence; the parts that broke were those asserted

most flatly.

An independent blind re-run of the balance sheet mapping, performed after the first was complete, found

four further defects that neither the original nor the critique had caught. It cost half a day.

The pattern is worth carrying into the build: a reader who has not seen your reasoning finds things a

reviewer who has cannot.